## Conceptualization
General Ideas | Node | Nodal State | Reference
Governance Structures | Institutional Support | Driven by NCC but little apparent support from HBRC | (Joyce, 2011)
| Path dependancy (BAU or deviation w or w/o support) | Refurbishes and expands existing structural defence | (NCC, 2018)
| Private property rights | On public property straddling NCC & HBRC Jurisdiction | (Beca, 2008)
| Transparency of decision making processes | Media covered the public noticing; included questions answered by engineers | (NCC, 2018) (HB Today Staff, 2010)
| Project spanning signular or multiple jurisdiction | Above and below MHWS so both NCC and HBRC involved | (Joyce, 2011)
| Temporal duration of institutional processes | engineering report in april 2008; planning started january 2009; consent still not approved by feb 2011 | (Joyce, 2011) (Beca, 2008) (NCC, 2018)
| Coordination across levels | poor coordination between councils - "An application to build the structure had been lodged with Hawke's Bay Regional Council, "but it is only a proposal at the moment, they could say no", Napier City Council chief executive Neil Taylor said." | (Joyce, 2011)
| Centralized / polycentric governance structures | poor coordination between councils - "An application to build the structure had been lodged with Hawke's Bay Regional Council, "but it is only a proposal at the moment, they could say no", Napier City Council chief executive Neil Taylor said." | (Joyce, 2011)
Leadership | Consistent leadership | NCC & Beca working on Westshore since 2003 | (Beca, 2003)
| Driver / project leader | NCC - "Napier City Council is planning to better protect this erosion-prone shoreline and property" | (NCC, 2018)
| Top down or bottom up decision making | Seems to be top down
BCA | Costs without action | Continued erosion - "As a further coastal defence measure, the existing seawall on the Westshore side of Whakarire Avenue was constructed in 1994. Built in concrete rubble, it was dressed with limestone rock armour in 1997, mainly on the leeward side. However, it is now considered not robust enough as a long-term structure to protect Whakarire Avenue. As it is, it funnels waves into the southern end of Westshore Beach, causing northward and seaward movement of sediment and renourishment material placed there." | (NCC, 2018)
| Who pays | NCC | (Dominion Post, 2009)
| Funding | NCC | (Dominion Post, 2009)
| Estimate of benefits and costs | "The two-year plan aims to transform the badly eroded area back into an attractive, sandy beach that could become a jewel in Napier's summer holiday destination crown. At present, the city does not have a good sandy beach - the Marine Pde beach is stony and often dangerous. "The future developments for Westshore beach are very exciting, not only for the local communities but also for visitors to the region," Hawke's Bay Inc tourism manager Kris Larner said yesterday." | (Dominion Post, 2009)
| Who is impacted | protects whakarire and maybe helps downdrift beaches | (Dominion Post, 2009)
Project Attributes | Technical quality of project/strategy | Well developed engineering report with wave impact analysis; peer reviewed by reputable scientist | (Komar, 2005)
| Technical resources for design (data + expertise) | Beach studied for at least 5 years by same engineering firm; previous reports by scientists | (Beca, 2008) (MetOcean Solutions, 2014) (Beca, 2003) (Komar, 2005)
| Community ability to influence | Options assessment was conducted with input from resildents | (Beca, 2008)
| Project reverse-ability | Project would not be easily reversed | (Beca, 2008)
| Uncertainties | Uncertainty in exact beach response and SLR; this amount of uncertainty is normal and accepted in coastal engineering | (Beca, 2008)
| Clear vision | Clear structure function and intended outputs | (Beca, 2008)
| Scale / size | Localized structure (140m) | (Beca, 2008)
Timing | Duration / time commitment / time of impacts | Construction approximately 5 month | (Beca, 2008)
| Project impetus (regulation, hazard event, etc.) | Erosion management and refurbishment of existing structure | (Beca, 2008)
Relationships and Interactions | Trust between communities, governments, technitions | Partnership between NCC and HBRC - "At the meeting a decision was made for the engineering advisors for both Napier City and Hawke’s Bay Regional Councils to jointly investigate other options for protecting the area"; "City council chief executive Neil Taylor had hoped the conflict would be resolved by now. An application to the Environment Court has been drafted but Mr Taylor was unsure if and when it would be filed. He said he had "no idea" where the discussions were at between the councils." ; Probably confident that stakeholders could get project knocked down given tanking of 2009 project - "Westshore resident Larry Dallimore said he has "won the fight but lost the war" in his attempts to see the best solution put in place for erosion along the coast." | (NCC, 2018) (Chatterton, 2012) (HB Today Staff, 2010)
| Coordination between public + private | Partnership between NCC and HBRC with Beca & T&T - "At the meeting a decision was made for the engineering advisors for both Napier City and Hawke’s Bay Regional Councils to jointly investigate other options for protecting the area" | (NCC, 2018) (Beca, 2014)
| Institutional trust | Low institutional trust given vocal stakeholders and misinformation | (Chatterton, 2013)
| Involvement of diverse groups | Engineers, heritage consultants, environmental consultants contracted by council | (Beca, 2014) (Barr, 2014) (MetOcean Solutions, 2014) (Smith, 2014)
| Community involvement | Seems little public consult done until July 2014 hearing | (Sharpe, 2014)
| NGO involvement | NGOs submitted opposing comments to consent but don't seem to have been involved pre-consent | (Chatterton, 2013)
Project Context | Competing interests / holistic strategy | Provides a feeder beach for Westshore nourishment | (Beca, 2014)
| Change required / Resistance to change | Would potentially effect surf break but continues defense | (Chatterton, 2013)
| Culutral / values-based context of project | Would potentially effect surfbreak and will infringe on ~20% of reef | (Chatterton, 2013) (MetOcean Solutions, 2014)
| Risk aversion / perception | Risk of impact to surf break percieved to be very high | (Chatterton, 2013)
| Political power / pressure / risk | Vocal stakeholders demanding protection | (Chatterton, 2013)(HB Today Staff, 2010)
| Knowledge of risks and responses | "In fact, as discussed in the next section, there has been minimal additional erosion along Westshore during the past century. Instead, the presence of the breakwater has provided significant protection to the Westshore community by having sheltered it from the dominant storm waves from the southeast, in large part accounting for its stability. These conclusions have not been well received by the inhabitants of Westshore, particularly by politicians who over the years have campaigned using the issue of the Port being the cause of Westshore’s perceived erosion problems." | (Komar, 2005)
| Communciation of project/strategy | One online article about project prior to meeting (not favorable). Wide swath of presenters at public meeting | (Chatterton, 2013) (Beca, 2014) (Barr, 2014) (MetOcean Solutions, 2014) (Smith, 2014)

## Engagement
TERMINATED IN CONCEPTAULIZATION

## Execution
TERMINATED IN CONCEPTAULIZATION